## Time Lines
Test Booth Timelines - 02-04-23
Milestones | Activity |  | Status | % Completion Status | Date Range | Days | Start Date | End Date | Status | Comments | Feedback
Milestone 1 | Screen Design | Application Screen Design |  |  |  | 2 | 2023-11-04
Milestone 1 | Screen Mapping - Testbooth Station | Operator screen functionalities and input fields |  |  |  | 1
Milestone 1 | Screen Mapping - Testbooth Master | Management Console Screen Design |  |  |  | 1
Milestone 1 | Application Work Flow Layout | Design Appicaition Work Flow and detailed User Flow | Planned | 0% |  | 1
Milestone 1 | Element List Mapping | List all the Input Fields, validations and relation | Planned | 0% |  | 1
Milestone 1 | Test Process sccreens | Tests Screen Card Designs | Planned | 0% |  | 2
Milestone 1 | PLC, Field devices and communication devices wiring testing | Electrical wiring testing |  |  |  | 1 |  | 18-4-23
Screen Development
Milestone 2 | Testbooth Library Development | Main Application Development - List all the tests, Add Edit Delete Functionality, backend | Planned | 0% |  | 1.5 | 19-4-23
|  | Database creation and Integration with Screens |  |  |  | 1
Milestone 2 | TestBooth Master Development - Screen Development & Data Base Integration -Database Design & Development | Main Application Development - List all the tests, Add Edit Delete Functionality, backend | Planned | 0% |  | 1.5
|  | Database creation and Integration with Screens | Planned | 0% |  | 1
|  | Screen Development |  |  |  | 1
Milestone 2 | PLC program development to aquire data from Yokogawa Energymeters through Modbus | Yokogawa Energy meter data acquisition to PLC |  |  |  | 2
Milestone 2 | PLC program development to aquire data from Analog Instruments | Analog Scaling program |  |  |  | 2
Milestone 2 | PLC registers mapping to the Application | Modbus registers Spreadsheet preparation |  |  |  | 2
Milestone 2 | PLC program testing for data acquisition from field devices | PLC program testing |  |  |  | 3
Milestone 2 | GOC to Neuron controller data transfer programming and testing | PLC logic |  |  |  | 2
Milestone 2 | Mitsubishi R PLC to GOC data transfer | PLC logic |  |  |  | 3
Milestone 2 | Data Mapping testing from PLC to Application | Data Mapping testing |  |  |  | 3 |  | 2023-05-05
2023-06-05
Milestone 3 | Modbus Connection | new expansion module communication check |  |  |  | 1
Milestone 3 | ISO Excel Sheet interation testing | mapping the excel cell to perticular function |  |  |  | 1
Milestone 3 | PLC registers Mapping | PLC data point name and register value |  |  |  | 1
Milestone 3 | database creation for PLC registers inputs |  |  |  |  | 1
Milestone 3 | LN data tables | getting specs form the LN server and validation -- need calirity |  |  |  | 1 |  | 2023-11-05
2023-12-05
Milestone 4 | Test Booth test Process Screens - Operator Screens | Test Booth Operator screen Development |  |  |  | 3
Milestone 4 | API Development | API Development for Operator screens |  |  |  | 4
Milestone 4 | Testbooth automatic process program development (it will vary based on the usage of Control valve) | Program Logic |  |  |  | 3
Milestone 4 | Validation popups | process validation process at the start |  | 0% |  | 0.5
Milestone 4 | Process skip and popup reason | process skip db update, reason popup, api | Planned | 0% |  | 1.5
Milestone 4 | Testbooth automatic process program testing |  |  |  |  | 3 |  | 27-5-23
|  |  | Planned | 0% | 26-8 | March April
Milestone 5 | DR screen development |  |  |  |  | 1 | 28-05-23
Milestone 5 | DR popup and API integration |  |  |  |  | 2
Milestone 5 | DR accept and decline popup api integration |  |  |  |  | 1
Milestone 5 | information pdf viewer |  |  |  |  | 1
Milestone 5 | information API integration |  |  |  |  | 1
Milestone 5 | Database finalization and Report Template preparation |  |  |  |  | 3
Milestone 5 | Reports Execution and testing |  |  |  |  | 2
Milestone 5 | Test certificates creation and testing |  |  |  |  | 4 |  | 2023-08-06
|  |  | Planned | 0% | 26-8 | March April
Milestone 6 | Operator Screen Configuration & Simulation for Multiple Stations |  | Planned | 0% |  | 1 | 2023-09-06
Milestone 6 | Application Testing |  | Planned | 0% |  | 2
Milestone 6 | Report Generation |  | Planned | 0% |  | 1
Milestone 6 | User Trials |  |  |  |  | 2
Milestone 6 | Application Handover and Go Live |  | Planned | 0%
Milestone 6 | Bug Fixing |  | Planned | 0% |  | 2
Milestone 6 | Support | [6 empty] | 15-06-23
Note on M2: Holi - Holiday -Hussain Hakimi

## Screen List
| TEST NAME | PROCESS DESCRIPTION | TYPE | Sequence No | Cycle Time | Source | Min/Max in Specification Table Excel | Remarks
SCREEN NO | OPERATOR LOGIN
1 |  | Operator Login Screen | Login
SCREEN NO | PREPARATION ACTIVITY
2 |  | FAB Number | Scan the FAB No |  |  |  |  | Check Scanned Fab No Status in Assembly Line. If Process Not Completed in any Assy then all pending process station popup will come.
|  | Model | Fetch FAB No Model Data from SQL DB
|  | TPL Number | Fetch FAB No TPL No Data from SQL DB
SCREEN NO | AIREND SPL NO
3 |  | Airend SPL no | Scanning or Manual Entry (Scanned Part No cross check with Assembly in SQL DB) | 1 | 10 |  |  | Check Scanned Part No Status in Assembly Line. If Part No Not Matched with Assy Data then Part No not matched popup will come.
SCREEN NO | OPERATOR CHECK
4 |  | Oil Filling | Submit | 1 | 10 |  |  | Submit Button Visible - Set time -3
|  | Outlet Motorized valve assy | Submit | 2 | 10 |  |  | Submit Button Visible - Set time -3
|  | Line Pressure Tube Fixing | Submit | 3 | 10 |  |  | Submit Button Visible - Set time -3
|  | Moisture drain hose fixing | Submit | 4 | 10 |  |  | Submit Button Visible - Set time -3
|  | Outlet hose fixing in Nozzle | Submit | 5 | 10 |  |  | Submit Button Visible - Set time -3
|  | Incoming Power Supply | Submit | 6 | 10 |  |  | Submit Button Visible - Set time -3
|  | Earth Wiring | Submit | 7 | 10 |  |  | Submit Button Visible - Set time -3
|  | Sump Pressure Hose assembly | Submit | 8 | 10 |  |  | Submit Button Visible - Set time -3
|  | RPM Sticker pasting in coupling | Submit | 9 | 10 |  |  | Submit Button Visible - Set time -3
|  | Position the RPM Sensor to the sticker | Submit | 10 | 10 |  |  | Submit Button Visible - Set time -3
SCREEN NO | MOTOR EFFICIENCY CLASS
5 |  | Main Motor Efficency / Class | Fetch From DB | 1 | 10 |  |  | Check Scanned Efficiency data in Assembly Line. If Not Matched with Assy Data then Not matched popup will come.
SCREEN NO | FAN MOTOR CURRENT MEASUREMENT
6 |  | Manual / Auto Selection | Auto/Manual Selection in Test Master Based on TPL No | 1 | 10 |  |  | Selection in Test Master
|  | Fan Motor Selection | 1 No/2 No's Selection in Test Master Based on TPL No | 2 | 10 |  |  | Selection in Test Master
|  | Single Phase Fan Motor Current | Single Phase Fan Motor - Manual Entry in Manual Mode (xx.xx) | 3 | 10 |  | LN Data (48) Max Only | Manual - Entry
|  | Single Phase Fan Motor Power | Single Phase Fan Motor - Manual Entry in Manual Mode (xx.xx) | 4 | 10
|  | 3 Phase Fan Motor | 3 Phase Fan Motor - Data Fetch From Energy Meter in Auto Mode | 5 | 10 |  | LN Data (48) Max Only | Auto - Fetch Data from EM
SCREEN NO | DRYER DATA CAPTURING
7 |  | Dryer Current (A) | Fetch data from Yokogawa Meter (xx.xx) | 1 | 10
|  | Dryer Power (KW) | Fetch data from Yokogawa Meter (xx.xx) | 2 | 10
|  | Dew point | Manual Entry from Neuron (xx.xx) | 3 | 10
|  | Gas Pressure | Manual entry from gauge in dryer (xx.xx) | 4 | 10
SCREEN NO | FULL OPEN TEST
8 |  | Ensure the ball condition (Full open) | Submit | 1 | 10
|  | Main Motor Rotation & Direction | Submit | 2 | 10 |  |  | Submit Button Visible - Set time -3
|  | Cooling Fan Motor Rotation & Direction | Submit | 3 | 10 |  |  | Submit Button Visible - Set time -3
|  | Neuron Controller Setting Change | Submit | 4 | 10 |  |  | Submit Button Visible - Set time -3
|  | MPV Setting | Acknowledge FB & Sump Pressure Sensor FB | 5 | 10 | AI-CH-0 | LN Data (58, 59)
|  | Safety Valve Checking | Submit | 6 | 10 |  |  | Submit Button Visible - Set time -3
|  | Change the safety valve setting with respect to model in neuron | Submit | 7 | 10 |  |  | Submit Button Visible - Set time -3
|  | Emergency Stop Check | Submit | 8 | 10 |  |  | Submit Button Visible - Set time -3
SCREEN NO | FULL CLOSE TEST
9 |  | Close motorized Valve to Full Close Condition | Submit | 1 | 10
|  | BDV Screw Cap removing | Submit | 2 | 10
|  | Blow down setting | Submit | 3 | 10 |  |  | Submit Button Visible - Set time -3
|  | Blow down screw cap fixing | Submit | 4 | 10 |  |  | Submit Button Visible - Set time -3
|  | Untold test-check for 5 min and standby mode | Compare Sump Pressure sensor FB with Minimum and Maximum | 5 | 10 | AI-CH-0
|  | Line Presssure (bar/psi) | Line Prssure Sensor FB (xx.xx) | 6 | 10 | AI-CH-2
|  | Sump Pressure (bar/psi) | Sump pressure Sensor FB (xx.xx) | 7 | 10 | AI-CH-0 | LN Data (54)
|  | Discharge Oil Temperature (Deg C) | Manual Entry & Submit (xx.xx) | 8 | 10
|  | Input Voltage (V) | Fetch data from Yokogawa Meter (xx.xx) | 9 | 10
|  | Current with fan (A) | Fetch data from Yokogawa Meter (xx.xx) | 10 | 10 | YM-Data-4
|  | Frequency (Hz) | Fetch data from Yokogawa Meter (xx.xx) | 11 | 10 | YM-Data-3
|  | Power with Fan Motor Current (A) | Fetch data from Yokogawa Meter (xx.xx) | 12 | 10 | YM-Data-2 | LN Data (49) Max Only
|  | Power Factor (Cos Phi) | Fetch data from Yokogawa Meter (xx.xx) | 13 | 10 | YM-Data-1
|  | Speed (RPM) | RPM Sesnor FB | 14 | 10 | AI-CH-3 | LN Data (17, 19)
SCREEN NO | PERFORMANCE TEST (LOAD TEST)
10 |  | Motor Speed | RPM Sesnor FB | 1 | 10 | AI-CH-3 | LN Data (17, 19) | Except Encap model, For others Motor Speed and airend speed are same
|  | Airend RPM | RPM Sesnor FB | 2 | 10 | AI-CH-3
|  | Volatge in R Phase | Fetch data from Yokogawa Meter (xx.xx) | 3 | 10
|  | Voltage in Y Phase | Fetch data from Yokogawa Meter (xx.xx) | 4 | 10
|  | Voltage in B Phase | Fetch data from Yokogawa Meter (xx.xx) | 5 | 10
|  | 3 Phase Voltage | Fetch data from Yokogawa Meter (xx.xx) | 6 | 10
|  | Intlet temperature (Air) | Temperature Sensor FB (xx.xx) & ISO Excel Input 04 | 7 | 10 | AI-CH-6
|  | Outlet Pressure (bar) | Line Prssure Sensor FB (xx.xx) & ISO excel Input 07 | 8 | 10 | AI-CH-2
|  | Sump Pressure (bar/psi) | Sump pressure Sensor FB (x.x) | 9 | 10 | AI-CH-0
|  | Input Voltage (V) | Fetch data from Yokogawa Meter (xx.xx) | 10 | 10
|  | Current with Fan (A) | Fetch data from Yokogawa Meter (xx.xx) | 11 | 10 | YM-Data-4
|  | Frequency (Hz) | Fetch data from Yokogawa Meter (xx.xx) | 14 | 10 | YM-Data-3
|  | package Input power measured | Fetch data from Yokogawa Meter (xx.xx)& ISO Excel Input 01 | 15 | 10 | YM-Data-2
|  | Inlet Pressure | Differential pressure Sensor FB & ISO Excel Input 06
|  | Ambient Temperature | FB from Temperature Sensor (xxx.xx) & ISO Excel Input 03
|  | Discharge Oil Temperature | Manual Entry & Submit (Data From Neuron) (xx.xx) | 16 | 10
|  | Upstream Pressure (P3) | Differential Pressure Sensor FB (xxx.x) & ISO Excel Input 08 (P3) | 17 | 10 | NP-CH-0
|  | Mano Meter reading (P3-P4)) | Differential Pressure Sensor FB (xxx.x) & ISO Excel Input 09 | 18 | 10 | NP-CH-1
|  | Temperature at Nozzle | Manual Entry (xxx.xx) & ISO Excel Sheet Input 05 | 19 | 10
|  | Relative Humidity | RH Meter FB & ISO Excel Sheet Input 10 | 20 | 10 | AI-CH-5
|  | Volume Flow rate correction (cfm) | From ISO Excel Sheet Output 04 (xx.xx) | 22 | 10
|  | Volume Flow rate correction (M³/sec) | From ISO Excel Sheet Output 03 (xx.xx) | 23 | 10
|  | Volume Flow rate correction (LPM) | From ISO Excel Sheet Output 05 (xx.xx) | 24 | 10
|  | Specific energy Consumption | From ISO Excel Sheet Output 02 (xx.xx) | 29 | 10 |  | LN Data (35)
|  | Isentrophic Eficiency | From ISO Excel Sheet Output 01 (xx.xx) | 30 | 10
|  | No Load Power | From Specification Sheet Output 08 (xx.xx) | 31 | 10 |  | LN Data (35)
SCREEN NO | BELT DRIVEN MODEL INPUTS
11 |  | Belt Efficiency | Manual Entry (xx.xx) | 1 | 10
SCREEN NO | VFD MODEL TESTING
12 |  | Voltage | Manual Entry (Data from Neuron) (xxx.x) | 1 | 10
|  | Current | Manual Entry (Data from Neuron) (xxx.xx) | 2 | 10
|  | Frequency | Manual Entry (Data from Neuron) (xxx.x) | 3 | 10
|  | Power | Manual Entry (Data from Neuron) (xxx.xx) | 4 | 10
|  | Speed | Manual Entry (Data from Neuron) (xxxxx) | 5 | 10
|  | Sump Prssure | FB from Sump Sensor (x.xx) | 6 | 10 | AI-CH-0
|  | Outlet Pressure | FB from line Sensor (xx.xx) & ISO Excel Input 07 | 7 | 10 | AI-CH-2
|  | Rotational frequency (Shaft Speed) - reading | FB from RPM Sensor (xxxxx) & ISO Excel Input 02 | 8 | 10 | AI-CH-3
|  | DOT | Manual Entry (Data from Neuron) (xxx.x) | 9 | 10 |  | LN Data (31, 32)
|  | Power factor | Fetch data from Yokogawa Meter (xx.xx) | 10 | 10 | YM-Data-1
|  | Package input power measured | Fetch data from Yokogawa Meter (xx.xx) &ISO Excel Input 01 | 11 | 10 | YM-Data-2
|  | Frequency | Fetch data from Yokogawa Meter (xx.xx) | 12 | 10 | YM-Data-3
|  | Current with Fan Motor | Fetch data from Yokogawa Meter (xx.xx) | 13 | 10 | YM-Data-4
|  | Input Volt | Fetch data from Yokogawa Meter (xx.xx) | 16 | 10
|  | Ambient Temperature | FB from Sensor (xxx.xx) & ISO Excel Input 03 | 17 | 10 | NP-CH-2
|  | Inlet Temperature | FB from Temperature Sensor (xxx.xx) & ISO Excel Input 04 | 18 | 10 | AI-CH-6
|  | Inlet Pressure | Differential pressure Sensor FB & ISO Excel Input 06
|  | Upstream Pressure (P3) | Differential Pressure Sensor FB (xxx.x) & ISO Excel Input 08 | 19 | 10 | NP-CH-0
|  | Mano Meter reading (P3-P4) | Differential Pressure Sensor FB (xxx.x) & ISO Excel Input 09 | 20 | 10 | NP-CH-1
|  | Temperature at Nozzle | FB from Sensor (xx.x) & ISO Excel Sheet Input 05 | 21 | 10 | AI-CH-4
|  | Realtive Humidity | From ISO Excel Sheet Input 10 | 22 | 10
|  | Ambient Temperature | FB from Sensor (xx.xx) & ISO Excel Input 03 | 23 | 10 | AI-CH-6
|  | Volume Flow rate correction (cfm) | From ISO Excel Sheet Output 04 (xx.x) | 24 | 10 |  | LN Data (20, 22)
|  | Volume Flow rate correction (M³/sec) | From ISO Excel Sheet Output 03 (x.xx) | 25 | 10 |  | LN Data (8, 10)
|  | Volume Flow rate correction (LPM) | From ISO Excel Sheet Output 05 (xx.xx) | 26 | 10
|  | Isentrophic Eficiency | From ISO Excel Sheet Output 01 | 27 | 10
|  | Specific energy Consumption | From ISO Excel Sheet Output 02 (xx.xx) | 32 | 10
3 Type of Matrix Table (SP, DP, TP) Available for This VFD Testing Refer Flow Chart for Details
SCREEN NO | VIBRATION MEASUREMENT
13 |  | Maximum Vibration | Manual Entry (xx.xx) | 1 | 10 |  | LN Data (40) Max Only
|  | Discharge Hose Vibration | Manual Entry (xx.xx) | 2 | 10
|  | Fan Vibration | Manual Entry (xx.xx) | 3 | 10
|  | SPM Reading in Top/ver+131:147tical dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 4 | 10 |  |  | Each Screen Should be consists of three numeric inputs (xx.xx,xx.xx,x.x) and colour code input in should be in drop down list which contains green,red and yellow
|  | SPM Reading in Top/vertical dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 5 | 10
|  | SPM Reading in Right Top dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 6 | 10
|  | SPM Reading in Right Top dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 7 | 10 |  |  |  | chrt
|  | SPM Reading in RHS dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 8 | 10
|  | SPM Reading in RHS dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 9 | 10
|  | SPM Reading in Right Bottom dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 10 | 10
|  | SPM Reading in Right Bottom dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 11 | 10
|  | SPM Reading in Left Top dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 12 | 10
|  | SPM Reading in Left Top dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 13 | 10
|  | SPM Reading in LHS dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 14 | 10
|  | SPM Reading in LHS dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 15 | 10
|  | SPM Reading in Left Bottom dBm 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 16 | 10
|  | SPM Reading in Left Bottom dBc 1. Value 2. Color 3. Carpet | Manual Entry (xx.xx) & should be in same screen | 17 | 10
|  | Thermal Image of Control Panel | Image Capturing & Submit | 18 | 10 |  |  | Thermal Imager image should be stored in server as Proof Image. Image captured using TABLET is stored in server as Actual Image. Proof Image and actual should be stored against FAB No. Image1 Name - ABCD123456_1 Image2 Name - ABCD123456_2 . . .
|  | Thermal Image of Contractor | Image Capturing & Submit | 19 | 10
|  | Thermal Image of Transformer | Image Capturing & Submit | 20 | 10
|  | Thermal Image of Motor Terminals | Image Capturing & Submit | 21 | 10
|  | Thermal Image of Motor Shaft | Image Capturing & Submit | 22 | 10
|  | Thermal Image of Male Rotor | Image Capturing & Submit | 23 | 10
|  | Thermal Image of Female Rotor | Image Capturing & Submit | 24 | 10
|  | Thermal Image of Scavenging line near Airend | Image Capturing & Submit | 25 | 10
|  | Thermal Image of Scavenging line near Tank | Image Capturing & Submit | 26 | 10
|  | Thermal Spare Image | Image Capturing & Submit | 27 | 10
|  | Thermal Spare Image | Image Capturing & Submit | 28 | 10
SCREEN NO | PARAMETERS TO BE DEFINED
14 |  | Oil recommended | From Specification Sheet output 29 | 1 | 10
|  | High Line Pressure tripping | From Specification Sheet output 40 | 2 | 10 |  | LN Data (51) Max Only | Test master to Display - operator will check - submit
|  | Line Pressure setting condition | From Specification Sheet output 41 | 3 | 10 |  |  | Submit
|  | Allowable Pressure drop (Sump to line) | From Specification Sheet output 42 | 4 | 10 |  | 0 | Test Master to Display - Set valve vs Actual Value comparision - if okay, Change next Screen
|  | No load sump pressure | From Specification Sheet output 43 | 5 | 10 |  | LN Data (54, 55) Max Only
|  | Oil carry over | From Specification Sheet Output 33 | 6 | 10
|  | Oil Inlet temperature | Manual Entry | 7 | 10
1 | Buttton Interlock Menu
2 | Button Visible Condition Menu
3 | All test Monitoring Process are standard and shows in a screen

## Testbooth Master
Screens
Test Booth
TM01 | Test Booth Library | [9 empty] | Test Booth Library
|  |  | Form | [7 empty] | Test Booth Master
Test Code
| Enter Value in Dropdown. |  | TEST NAME |  |  | Dropdowns for Test Name |  |  |  |  | Test 1 | A, B, C
|  |  | TEST NAME Seq |  |  | Cycle Time |  |  |  |  | Test 2 | X, Y, Z
PROCESS DESCRIPTION
|  |  | TYPE |  | Add | Edit | Delete
|  |  | export options |  |  |  | search
List of all the test process
ACTICE TEST PROCESS
[14 empty] | Add | Edit | Delete
[11 empty] | OPERATOR CHECK |  |  | OPERATOR CHECK
[12 empty] | Oil Filling | Submit |  | Oil Filling | Submit
TM02 | Test Booth Master | [10 empty] | Outlet Motorized valve assy | Submit |  | Outlet Motorized valve assy | Submit
[12 empty] | Line Pressure Tube Fixing | Submit |  | Line Pressure Tube Fixing | Submit
|  |  | Form | [8 empty] | Moisture drain hose fixing | Submit |  | Moisture drain hose fixing | Submit
Test Code | Test Code TPL No. |  | Test Code | [8 empty] | Outlet hose fixing in Nozzle | Submit |  | Outlet hose fixing in Nozzle | Submit
Active Test | Active Test TPL No. |  | Tpl No |  |  | actiive test tpl no | [5 empty] | Incoming Power Supply | Submit |  | Incoming Power Supply | Submit
|  |  | seq no |  |  | test code / active test | [5 empty] | Earth Wiring | Submit |  | Earth Wiring | Submit
[5 empty] | Add | Edit | Delete |  |  |  |  | Sump Pressure Hose assembly | Submit |  | Sump Pressure Hose assembly | Submit
[12 empty] | RPM Sticker pasting in coupling | Submit |  | RPM Sticker pasting in coupling | Submit
|  |  | List of all the actiive test process | [8 empty] | Position the RPM Sensor to the sticker | Submit |  | Position the RPM Sensor to the sticker | Submit
TM03 | Test TPLs Validations | [5 empty] | notifications | Logout
|  | Emp Name | [8 empty] | TM11 | initial validation Popup
Emp ID
Skill Level
All Process Not Completed
scan
TPL no
|  | Fab No | [13 empty] | OK
TM04 | Test Process cards
[7 empty] | notifications | Logout
|  | Emp Name |  | TPL No |  |  |  | Cycle time
|  | Emp ID |  | Fab No |  |  |  | 0:00
|  | Skill Level |  | Group |  |  |  | Actual Time
|  | Test Description | [5 empty] | 0:00
|  | Test Type | Total Test | Completed Test | Input Type |  | Process Skip
|  | operator check | 12 | 3 | submit
Submit
image
information
| TM05 | Submit | [6 empty] | TM08 | Pass to DR Popup
|  |  | Submit | [7 empty] | reason | input entry
Bypass
| TM06 | Manual Entry
|  | Process desc | Manual entry
[9 empty] | TM09 | [5 empty] | notifications | Logout
Emp Name
Emp ID
Skill Level
| TM07a | Sump pressure | 10 | 100
|  |  | Min Value | Max Value
|  | Sump pressure | readonly |  | units | 60 SEC |  |  |  | TPL no | Fab No | parameter | value | TP_NO | Operator_Name | Reason
pass to DR
| TM07b | Atmospheric Pressure
|  |  | Min Value | Max Value
|  | Atmospheric Pressure | readonly |  | units
pass to DR
[9 empty] | TM10 | popup on selectin tpl
| TM07c | Line pressure
|  |  | Min Value | Max Value
[11 empty] | reason | input entry
|  | Line pressure | readonly |  | units
pass to DR
[12 empty] | Accept | Decline | restart
| TM07d | RPM Meter | plc/manual entry
|  |  | Min Value | Max Value
[9 empty] | TM12 | Process skip Popup
|  | RPM Meter | readonly |  | units
reason
[5 empty] | pass to DR | [5 empty] | input
| TM07e | Humidity | plc/manual entry
|  |  | Min Value | Max Value
OK
|  | Humidity | readonly |  | units
pass to DR
| TM07f | Air Inlet Temperature | plc/manual entry
|  |  | Min Value | Max Value
|  | Air Inlet Temperature | readonly |  | units
pass to DR
| TM07g | Differential Pressure (P3) | plc/manual entry
|  |  | Min Value | Max Value
|  | Differential Pressure (P3) | readonly |  | units
| TM07h | Differential Pressure (P3-P4)
|  |  | Min Value | Max Value
|  | Differential Pressure (P3-P4) | readonly |  | units
pass to DR
| TM07i | Air OutletTemperature
|  |  | Min Value | Max Value
|  | Air OutletTemperature | readonly |  | units
pass to DR
| TM07j | Power Factor
|  |  | Min Value | Max Value
|  | Power Factor | readonly |  | units
pass to DR
| TM07k | Power with fan motor | plc/manual entry
|  |  | Min Value | Max Value
|  | Power with fan motor | readonly |  | units
pass to DR
| TM07l | Frequency | plc/manual entry
|  |  | Min Value | Max Value
|  | Frequency | readonly |  | units
pass to DR
| TM07m | Current with fan motor | plc/manual entry
|  |  | Min Value | Max Value
|  | Current with fan motor | readonly |  | units
pass to DR
| TM07n | R Phase | plc/manual entry
|  |  | Min Value | Max Value
|  | R Phase | readonly |  | units
| TM07o | Y Phase
|  |  | Min Value | Max Value
|  | Y Phase | readonly |  | units
pass to DR
| TM07p | B Phase
|  |  | Min Value | Max Value
|  | B Phase | readonly |  | units
pass to DR
| TM07q | 3 Phase Input Voltage
|  |  | Min Value | Max Value
|  | 3 Phase Input Voltage | readonly |  | units
pass to DR
| TM07r | Analog Inputs | plc/manual entry
|  |  | Min Value | Max Value
|  | Analog Inputs | readonly |  | units
pass to DR
| TM07s | Power Meter Parameters | plc/manual entry
|  |  | Min Value | Max Value
|  | Power Meter Parameters | readonly |  | units
pass to DR
Note on D5: input
Note on D6: dropdown test 1 test 2 People should be able to Type in it.
Note on D7: input
Note on G7: input
Note on D8: input
Note on D9: dropdown
Note on D25: dropdown
Note on G25: input
Note on D26: dropdown
Note on G26: input
Note on D27: input
Note on G27: radio button
Note on B63: Operator Screens -Hussain Hakimi
Note on H77: image only for submit button -Hussain Hakimi
Note on H81: to be on all screen -Hussain Hakimi
Note on D107: from plc
Note on D116: from plc
Note on D125: from plc
Note on D134: from plc
Note on D143: from plc
Note on D152: from plc
Note on D161: from plc
Note on D170: from plc
Note on D179: from plc
Note on D188: from plc
Note on D197: from plc
Note on D206: from plc
Note on D215: from plc
Note on D224: from plc
Note on D233: from plc
Note on D242: from plc
Note on D251: from plc
Note on D260: from plc
Note on D269: from plc

## Sheet16
Test Code | TEST NAME | TEST NAME Seq | PROCESS DESCRIPTION | TYPE | Cycle Time | TEST PROseq no
TEST1 | OPER CHEC | 1 | OL | SUMI | 10 | 1
TEST2 | OPER CHEC | 1 | OL1 | SUMI | 10 | 2
TEST3 | OPER CHEC | 1 | OL2 | SUMI | 10 | 3
TEST4 | FULL | 2 | OL3 | SUMI | 10 | 1
TEST5 | FULL | 2 | OL4 | SUMI | 10 | 2
TEST6 | FULL | 2 | OL5 | SUMI | 10 | 3
TEST1 | OPER CHEC | 1 | OL | SUMI | 10 | 3
Note on B4: input
Note on C4: dropdown
Note on D4: dropdown
Note on E4: input
Note on F4: dropdown
Note on G4: input
Note on H4: dropdown

## Process
Step 1 | Admin Login
View list of TPL ready for test
Step 2 | Create Test Group | Add Edit Delete Duplicate
Step 3 | Assign Test group to TPL | Add Edit Delete Duplicate
Step 4 | Operator Login
Step 5 | Scan the Fab no | Refer Screen For complete Process
Step 6 | Complete tests as per the timeline | Refer Screen For complete Process
Step 7 | Logout | Refer Screen For complete Process
Reports
Step 8
Step 1 | Data Released from LN server | to Digital factory server | 420 columns | seperate LN tables for testbooth
we get min max value from LN server
| Admin Logs in | Asset Screen | Testbooth Library
Functionality
| Create a test process - and Sequence | Then he will go to test booth Master | He will assign a sequence to the TPL number, he will also create a tet squence
Step 2 | Operator Logs in | Screen to scan the QR Code | We will check for all the process to be completed | Rework Station | Test Process will start
Contniue with test
Test Cards flow |  | Submit | Only time validation
manual Entry and submit
Sump Pressure

## Process - Steps
Step 1 | Admin Login
| Login Screen | [6 empty] | Admin Login (same credentials) to the console currently used for the Assembly line will be used. Login screen has been developed
User Name
Password
Step 2 | Testbooth Asset Library |  |  | testbooth library | testbooth master |  |  | Admin goes to the Testbooth Asset library Link in the "left navigation menu". There will be 2 tabs. Selects tab "Test Booth Library". Admin will create Test Process sequentially. Assign cycle time. Give it a unique testcode.
| TM01 | Menu | Form
| Test Booth Library | testbooth | Test Code
|  |  | TEST NAME |  |  | Dropdowns for Test Name
|  |  | TEST NAME Seq |  |  | Cycle Time
PROCESS DESCRIPTION
|  |  | TYPE |  | Add | Edit | Delete
List of all the test codes
|  |  |  | Test Codes | Test Name | Cycle Time | Type/Desc/seq
1
2
3
4
5
Step 3 | Testbooth Asset Library |  |  | Tab1 | Tab2 |  |  | Tab2 - Admin will assign TPL no the Testcode. Can
| TM02 | Menu
| Test Booth Master |  | Form
Test Code
|  |  | Tpl No |  |  | actiive test tpl no
process code / active test
|  |  | seq no |  | Add | Edit | Delete
List of all the active test Names
Test Name
|  |  | 1 | DRYER DATA CAPTURING
|  |  | 2 | FAN MOTOR CURRENT MEASUREMENT
|  |  | 3 | FULL CLOSE TEST
|  |  | 4 | FULL OPEN TEST
MOTOR EFFICIENCY CLASS
OPERATOR CHECK
PARAMETERS TO BE DEF
Note on D19: input
Note on D20: dropdown DRYER DATA CAPTURING FAN MOTOR CURRENT MEASUREMENT FULL CLOSE TEST FULL OPEN TEST MOTOR EFFICIENCY CLASS OPERATOR CHECK PARAMETERS TO BE DEFINED PERFORMANCE TEST (LOAD TEST) VFD MODEL TESTING VIBRATION MEASUREMENT
Note on D21: dropdown 1 2 3 4
Note on G21: input Based on the Test name this depended drop down will appear.
Note on D22: input/dropdown
Note on D23: dropdown Submit Manual Entry Sump pressure Atmospheric Pressure 27 Types
Note on D39: dropdown
Note on G39: input
Note on D40: Dropdown
Note on G40: input
Note on D41: dropdown/input
Note on G41: radio button
Note on D42: dropdown

## Data Flow
SENARIO - 1 | Programming in Django
SENARIO - 2 | Programming in PLC

## Reports
List of Reports
Types | Templates
8 types for test certificate
Performance test report FAB wise
VFD turn down Test report FAB wise
Consolidate test report with date filter
Statistical process control graph for all Individual parameters

## Sheet12
[6 empty] | FAN MOTOR CURRENT MEASUREMENT | FAN MOTOR CURRENT MEASUREMENT | VFD MODEL TESTING | OPERATOR CHECK
TPL Number | Test Type | Process Description | Input Type (Fixed) | Process Sequence No | Process Cycle Time | Fan Motor Current Measurement | Number of Fan's | VFD Model Testing | Oil Recommended | VFD | Dryer | Belt Driven | SPM Reading Color
Drop Down | Drop Down List | Manual Entry | Drop Down List | Manual Entry | Manual Entry | Drop Down List | Drop Down List | Drop Down List | Drop Down | Drop Down | Drop Down | Drop Down | Drop Down
- | Option - Add/Delete/Modify | Option - Add/Delete/Modify | - | - | - | - | - | Option - Add/Delete/Modify | Option - Add/Delete/Modify | - | - | - | -
Fetch TPL No From TPL Master | Fan Motor Current Measurement |  | Submit |  |  | Auto Mode | 1 | 50 Hz Single Pressure | Elgi Airlube | Yes | Yes | Yes | Green
| Dryer Data Capturing |  | Manual Entry |  |  | Manual Mode | 2 | 50 Hz Dual Pressure | Synthetic Oil | No | No | No | Yellow
| Full Open Test |  | Sump pressure |  |  |  |  | 50 HzTriple Pressure | Synthetic Plus Oil |  |  |  | Red
| Full Close Test |  | Atmospheric Pressure |  |  |  |  | 60 Hz Single Pressure
| Performance Test (Load Test) |  | Line pressure |  |  |  |  | 60 Hz Dual Pressure
| Belt Driven Model Inputs |  | RPM Meter |  |  |  |  | 60 HzTriple Pressure
| VFD Model Testing |  | Humidity
| Vibration Measurement |  | Air Inlet Temperature
| Parameters to be Defined |  | Differential Pressure (P3)
Differential Pressure (P3-P4)
Air OutletTemperature
Power Factor
Power with fan motor
Frequency
Current with fan motor
R Phase
Y Phase
B Phase
3 Phase Input Voltage
Analog Inputs
Power Meter Parameters
Submit
Submit
|  | Manual Entry |  |  |  |  | tpl no | fab no | prooc desc | cycle time | process type | status
[7 empty] | tpl11 | fab123 | p1 | p2 | p3
[7 empty] | tpl11 | fab123 | p2
|  | Process desc | Manual entry |  |  |  | tpl11 | fab123 | p3
[7 empty] | tpl11 | fab123 | p4
[7 empty] | tpl11 | fab123 | p5
[7 empty] | tpl11 | fab123 | p6
[7 empty] | tpl11 | fab123 | p7
[7 empty] | tpl11 | fab123 | p8
|  | Sump pressure |  |  |  |  | tpl11 | fab123 | p9
[7 empty] | tpl11 | fab123 | p10
[7 empty] | tpl11 | fab123 | p11
|  | Sump pressure | readonly |  | bar
Atmospheric Pressure
|  | Atmospheric Pressure | readonly
time?
|  |  | Accept | Decline
Line pressure
|  | Line pressure | readonly
|  | RPM Meter | plc/manual entry
|  | RPM Meter | readonly
|  | Humidity | plc/manual entry
|  | Humidity | readonly
|  | Humidity | plc/manual entry
|  | Humidity | readonly
|  | Air Inlet Temperature | plc/manual entry
|  | Air Inlet Temperature | readonly
Note on D56: from plc
Note on D65: from plc
Note on D74: from plc
Note on D83: from plc
Note on D92: from plc
Note on D101: from plc
Note on D110: from plc